## ProjectSchedule
UW Results Frequency Project
Centron
Richard Yoon / Jeremy Aschenbrenner |  |  | Project Start: | 2018-04-23
|  |  | Display Week: | 1 |  |  | 2018-04-23 | [6 empty] | 2018-04-30 | [6 empty] | 2018-05-07 | [6 empty] | 2018-05-14 | [6 empty] | 2018-05-21 | [6 empty] | 2018-05-28 | [6 empty] | 2018-06-04 | [6 empty] | 2018-06-11
 | time axis 2018-04-23 to 2018-06-17
TASK | ASSIGNED TO | EST DURATION | PROGRESS | START | END | DAYS | time axis 2018-04-23 to 2018-06-17
Planning
Complete Planning | Richard / BA | 5 | 0% | 2018-04-23 | 2018-04-27 | 5
Requirements / Design
Account Login | BA | 1.3333 | 0% | 2018-04-30 | 2018-04-30 | 1
Forgotten Password | BA | 1 | 0% | 2018-05-01 | 2018-05-01 | 1
Load Leads | BA | 4.1667 | 0% | 2018-05-02 | 2018-05-07 | 6
Update Leads | BA | 2.3333 | 0% | 2018-05-08 | 2018-05-09 | 2
Lead Search | BA | 2 | 0% | 2018-05-10 | 2018-05-11 | 2
View Lead | BA | 3.8333 | 0% | 2018-05-14 | 2018-05-17 | 4
Export Report Data | BA | 3.1667 | 0% | 2018-05-18 | 2018-05-22 | 5
UW Report | BA | 5.5 | 0% | 2018-05-23 | 2018-05-30 | 8
Export Lead Data | BA | 3.1667 | 0% | 2018-05-31 | 2018-06-04 | 5
Lead File | BA | 4 | 0% | 2018-06-05 | 2018-06-08 | 4
Development
Load Leads | Dev2 | 15.8333 | 0% | 2018-06-01 | 2018-06-22 | 22
Account Login | Dev1 | 3.1667 | 0% | 2018-06-18 | 2018-06-20 | 3
Update Leads | Dev1 | 3.6667 | 0% | 2018-06-21 | 2018-06-26 | 6
Lead Search | Dev2 | 3.1667 | 0% | 2018-06-25 | 2018-06-27 | 3
View Lead | Dev1 | 3.1667 | 0% | 2018-06-27 | 2018-06-29 | 3
Export Lead Data | DBA | 3 | 0% | 2018-06-25 | 2018-06-27 | 3
Lead File | Dev2 | 3.8333 | 0% | 2018-06-28 | 2018-07-03 | 6
Export Report Data | DBA | 3 | 0% | 2018-06-28 | 2018-07-02 | 5
UW Report | Dev1 | 9.8333 | 0% | 2018-07-06 | 2018-07-19 | 14
Testing
Account Login | BA | 1.1667 | 0% | 2018-07-23 | 2018-07-23 | 1
Forgotten Password | BA | 1 | 0% | 2018-07-24 | 2018-07-24 | 1
Load Leads | BA | 7.6667 | 0% | 2018-07-25 | 2018-08-03 | 10
Update Leads | BA | 1.1667 | 0% | 2018-08-06 | 2018-08-06 | 1
Lead Search | BA | 2.8333 | 0% | 2018-08-07 | 2018-08-09 | 3
View Lead | BA | 2 | 0% | 2018-08-10 | 2018-08-13 | 4
UW Report | BA | 5.5 | 0% | 2018-08-14 | 2018-08-21 | 8
Lead File | BA | 4.5 | 0% | 2018-08-22 | 2018-08-28 | 7
Training
Train the Trainer (Prep) | BA | 4 | 0% | 2018-08-30 | 2018-09-05
Train the Trainer (Conduct) | BA | 2 | 0% | 2018-09-06 | 2018-09-07
Train Sales Support (Prep) | Sales Mgr | 2 | 0% | 2018-09-10 | 2018-09-11 | 2
Train Sales Associates (Prep) | Sales Mgr | 3 | 0% | 2018-09-12 | 2018-09-14 | 3
Train Sales Support (Conduct) | Sales Mgr | 2 | 0% | 2018-09-17 | 2018-09-18 | 2
Train Sales Associates (Conduct) | Sales Mgr | 3 | 0% | 2018-09-19 | 2018-09-21 | 3
Implementation
Implement Processes & System | Dev | 5 | 0% | 2018-09-24 | 2018-09-28 | 5
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Note on I6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.
Note on G48: 12/25 holiday