## ProjectSchedule
UW Results Frequency Project
Centron
Richard Yoon / Jeremy Aschenbrenner |  |  | Project Start: | 2018-04-23
|  |  | Display Week: | 1 |  |  | 2018-04-23 | [6 empty] | 2018-04-30 | [6 empty] | 2018-05-07 | [6 empty] | 2018-05-14 | [6 empty] | 2018-05-21 | [6 empty] | 2018-05-28 | [6 empty] | 2018-06-04 | [6 empty] | 2018-06-11
 | time axis 2018-04-23 to 2018-06-17
TASK | ASSIGNED TO | EST DURATION | PROGRESS | START | END | DAYS | time axis 2018-04-23 to 2018-06-17
Planning
Complete Planning | Richard / BA | 5 | 0% | 2018-04-23 | 2018-04-27 | 5
Requirements / Design
Account Login | BA | 1.3333 | 0% | 2018-05-02 | 2018-05-02 | 1
Forgotten Password | BA | 1 | 0% | 2018-05-09 | 2018-05-09 | 1
Load Leads | BA | 4.1667 | 0% | 2018-05-10 | 2018-05-15 | 6
Update Leads | BA | 2.3333 | 0% | 2018-05-18 | 2018-05-21 | 4
Lead Search | BA | 2 | 0% | 2018-05-24 | 2018-05-25 | 2
View Lead | BA | 3.8333 | 0% | 2018-05-28 | 2018-05-31 | 4
Export Report Data | BA | 3.1667 | 0% | 2018-06-01 | 2018-06-05 | 5
UW Report | BA | 5.5 | 0% | 2018-06-06 | 2018-06-13 | 8
Export Lead Data | BA | 3.1667 | 0% | 2018-06-14 | 2018-06-18 | 5
Lead File | BA | 4 | 0% | 2018-06-19 | 2018-06-22 | 4
Development
Manage Accounts | Dev | 4.6667 | 0% | 2018-07-05 | 2018-07-11 | 7
Account Login | Dev | 3.1667 | 0% | 2018-07-12 | 2018-07-16 | 5
Account Security Access | Dev | 8 | 0% | 2018-07-17 | 2018-07-26 | 10
Load Leads | Dev | 15.8333 | 0% | 2018-07-27 | 2018-08-17 | 22
Assign Leads | Dev | 2 | 0% | 2018-08-20 | 2018-08-21 | 2
Update Leads | Dev | 3.6667 | 0% | 2018-08-22 | 2018-08-27 | 6
Reassign Leads | Dev | 2.1667 | 0% | 2018-08-28 | 2018-08-29 | 2
Lead Search | Dev | 3.1667 | 0% | 2018-08-30 | 2018-09-04 | 6
View Lead | Dev | 3.1667 | 0% | 2018-09-05 | 2018-09-07 | 3
Export Report Data | Dev | 3 | 0% | 2018-09-10 | 2018-09-12 | 3
UW Report | Dev | 9.8333 | 0% | 2018-09-13 | 2018-09-26 | 14
Export Lead Data | Dev | 3 | 0% | 2018-09-27 | 2018-10-01 | 5
Lead File | Dev | 3.8333 | 0% | 2018-10-02 | 2018-10-05 | 4
Testing
Manage Accounts | BA | 2.1667 | 0% | 2018-10-08 | 2018-10-09 | 2
Account Login | BA | 1.1667 | 0% | 2018-10-10 | 2018-10-10 | 1
Account Security Access | BA | 2 | 0% | 2018-10-11 | 2018-10-12 | 2
Forgotten Password | BA | 1 | 0% | 2018-10-15 | 2018-10-15 | 1
Load Leads | BA | 7.6667 | 0% | 2018-10-16 | 2018-10-25 | 10
Assign Leads | BA | 1.1667 | 0% | 2018-10-26 | 2018-10-26 | 1
Update Leads | BA | 1.1667 | 0% | 2018-10-29 | 2018-10-29 | 1
Reassign Leads | BA | 1.1667 | 0% | 2018-10-30 | 2018-10-30 | 1
Lead Search | BA | 2.8333 | 0% | 2018-10-31 | 2018-11-02 | 3
View Lead | BA | 2 | 0% | 2018-11-05 | 2018-11-06 | 2
UW Report | BA | 5.5 | 0% | 2018-11-07 | 2018-11-14 | 8
Lead File | BA | 4.5 | 0% | 2018-11-15 | 2018-11-21 | 7
Training
Train the Trainer (Prep) | BA | 4 | 0% | 2018-11-22 | 2018-11-27
Train the Trainer (Conduct) | BA | 2 | 0% | 2018-11-28 | 2018-11-30
Train Sales Support (Prep) | Sales Mgr | 3 | 0% | 2018-12-03 | 2018-12-05 | 3
Train Sales Associates (Prep) | Sales Mgr | 3 | 0% | 2018-12-06 | 2018-12-10 | 5
Train Sales Support (Conduct) | Sales Mgr | 3 | 0% | 2018-12-11 | 2018-12-13 | 3
Train Sales Associates (Conduct) | Sales Mgr | 3 | 0% | 2018-12-14 | 2018-12-18 | 5
Implementation
Implement Processes & System | Dev | 5 | 0% | 2018-12-19 | 2018-12-26 | 8
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Note on I6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.
Note on F22: closed 7/2-7/4 for holiday
Note on G29: 9/3 holiday
Note on G56: 12/25 holiday