## Sprint Schedule
Project Sprint Schedule This document is to be used to lay out the anticipated schedule for the project.
Task | Duration | Start | End | Comments
Sprint 1 | 14 days | 2018-08-01 | 2018-08-14
Sprint 1 Planning | 1 day | 2018-08-01 | 2018-08-01 | User story commitment and task creation
Sprint 1 Development | 12 days | 2018-08-02 | 2018-08-13 | Features created, tested, and demonstrated
Sprint 1 Feature Review | 1 day | 2018-08-14 | 2018-08-14 | Features reviewed
Sprint 2 | 14 days | 2018-08-15 | 2018-08-28
Sprint 2 Planning and Retrospective | 1 day | 2018-08-15 | 2018-08-15 | User story commitment, task creation, and previous sprint retrospective
Sprint 2 Development | 12 days | 2018-08-16 | 2018-08-27 | Features created, tested, and demonstrated
Sprint 2 Feature Review | 1 day | 2018-08-28 | 2018-08-28 | Features reviewed
Sprint 3 | 14 days | 2018-08-29 | 2018-09-11
Sprint 3 Planning and Retrospective | 1 day | 2018-08-29 | 2018-08-29 | User story commitment, task creation, and previous sprint retrospective
Sprint 3 Development | 11 days | 2018-08-30 | 2018-09-09 | Features created, tested, and demonstrated
Sprint 3 Feature Review | 1 day | 2018-09-10 | 2018-09-10 | Features reviewed
Sprint 1-3 Release | 1 day | 2018-09-11 | 2018-09-11 | Release of completed deliverables
Sprint 4 | 14 days | 2018-09-12 | 2018-09-25
Sprint 3 Planning and Retrospective | 1 day | 2018-09-12 | 2018-09-12 | User story commitment, task creation, and previous sprint retrospective
Sprint 4 Development | 12 days | 2018-09-13 | 2018-09-24 | Features created, tested, and demonstrated
Sprint 4 Feature Review | 1 day | 2018-09-25 | 2018-09-25 | Features reviewed
Sprint 5 | 14 days | 2018-09-26 | 2018-10-09
Sprint 5 Planning and Retrospective | 1 day | 2018-09-26 | 2018-09-26 | User story commitment, task creation, and previous sprint retrospective
Sprint 5 Development | 12 days | 2018-09-27 | 2018-10-08 | Features created, tested, and demonstrated
Sprint 5 Feature Review | 1 day | 2018-10-09 | 2018-10-09 | Features reviewed
Sprint 6 | 14 days | 2018-10-10 | 2018-10-23
Sprint 6 Planning and Retrospective | 1 day | 2018-10-10 | 2018-10-10 | User story commitment, task creation, and previous sprint retrospective
Sprint 6 Development | 11 days | 2018-10-11 | 2018-10-21 | Features created, tested, and demonstrated
Sprint 6 Feature Review | 1 day | 2018-10-22 | 2018-10-22 | Features reviewed
Sprint 4-6 Release | 1 day | 2018-10-23 | 2018-10-23 | Release of completed deliverables
Sprint 7 | 14 days | 2018-10-24 | 2018-11-06
Project Documentation | 12 days | 2018-10-24 | 2018-11-04 | Create user manuals, support documentation, and necessary technical specs
Project Retrospective | 2 days | 2018-11-05 | 2018-11-06 | Final review of the project and determines any necessary next steps
Template provided courtesy of The BA Guide
www.TheBAGuide.com