## PERT
PERT Worksheet This worksheet is used to assist in estimating project activities
Activity | Optimistic | Most Likely | Pessimistic | PERT Estimate | Activity Type | Tasks | Notes
Account Login | 1 | 1 | 3 | 1.3333 | 1 - Requirements/Design | ∙ Define process ∙ Design login UI | For users and admins to gain access to the system
Account Login | 2 | 3 | 5 | 3.1667 | 2 - Development | ∙ Develop login UI ∙ Create login validation check | For users and admins to gain access to the system
Account Login | 1 | 1 | 2 | 1.1667 | 3 - Testing | ∙ Test login UI ∙ Test login validation | For users and admins to gain access to the system
Account Security Access | 2 | 3 | 7 | 3.5 | 1 - Requirements/Design | ∙ Define admin only items ∙ Design UI changes to accommodate ∙ Design functionality changes to accommodate | Items identified made accessible only by admins
Account Security Access | 2 | 7 | 18 | 8 | 2 - Development | ∙ Write login query for access level ∙ Develop UI changes based on access ∙ Develop functionality changes based on access | Items identified made accessible only by admins
Account Security Access | 1 | 2 | 3 | 2 | 3 - Testing | ∙ Test UI changes ∙ Test account access (permissions) | Items identified made accessible only by admins
Assign Leads | 1 | 2 | 3 | 2 | 1 - Requirements/Design | ∙ Define process ∙ Design lead assignment UI | Assign leads out to sales reps
Assign Leads | 1 | 2 | 3 | 2 | 2 - Development | ∙ Develop lead assignment UI ∙ Develop lead assignment function | Assign leads out to sales reps
Assign Leads | 1 | 1 | 2 | 1.1667 | 3 - Testing | ∙ Test lead assignment UI ∙ Test lead assignment function | Assign leads out to sales reps
Export Lead Data | 2 | 3 | 5 | 3.1667 | 1 - Requirements/Design | ∙ Define process ∙ Identify data | Pull data needed for lead file
Export Lead Data | 2 | 3 | 4 | 3 | 2 - Development | ∙ Create queries | Pull data needed for lead file
Export Report Data | 2 | 3 | 5 | 3.1667 | 1 - Requirements/Design | ∙ Define process ∙ Identify data | Pull data needed for report
Export Report Data | 2 | 3 | 4 | 3 | 2 - Development | ∙ Create queries | Pull data needed for report
Forgotten Password | 1 | 1 | 1 | 1 | 1 - Requirements/Design | ∙ Define process | Manual process to request password reset
Forgotten Password | 1 | 1 | 1 | 1 | 3 - Testing | ∙ Validate process | Manual process to request password reset
Lead File | 1 | 2 | 3 | 2 | 1 - Requirements/Design | ∙ Design format | Create Lead File to send to the client (sending is manual)
Lead File | 2 | 4 | 5 | 3.8333 | 2 - Development | ∙ Transform data ∙ Create file ∙ Create ability to run file | Create Lead File to send to the client (sending is manual)
Lead File | 3 | 4 | 8 | 4.5 | 3 - Testing | ∙ Test ability to run file ∙ Test file format ∙ Validate accurate results | Create Lead File to send to the client (sending is manual)
Lead Search | 1 | 2 | 3 | 2 | 1 - Requirements/Design | ∙ Identify search criteria ∙ Design search UI | Ability to search for a lead
Lead Search | 2 | 3 | 5 | 3.1667 | 2 - Development | ∙ Develop search UI ∙ Develop ability to select a lead | Ability to search for a lead
Lead Search | 1 | 3 | 4 | 2.8333 | 3 - Testing | ∙ Test search UI ∙ Test ability to select a lead | Ability to search for a lead
Load Leads | 3 | 4 | 6 | 4.1667 | 1 - Requirements/Design | ∙ Define process ∙ Identify data ∙ Design lead load UI ∙ Design load status output | Get the leads from the file into the system
Load Leads | 7 | 15 | 28 | 15.8333 | 2 - Development | ∙ Database design ∙ Create database ∙ Develop lead load UI ∙ Generate load status output | Get the leads from the file into the system
Load Leads | 4 | 8 | 10 | 7.6667 | 3 - Testing | ∙ Test lead load UI ∙ Test lead load functionality ∙ Test load status output | Get the leads from the file into the system
Manage Accounts | 1 | 2 | 4 | 2.1667 | 1 - Requirements/Design | ∙ Define process ∙ Design manage accounts UI | Administrators ability to manage accounts (create, activate, deactivate, update, change access)
Manage Accounts | 2 | 4 | 10 | 4.6667 | 2 - Development | ∙ Develop manage accounts UI ∙ Develop create account function ∙ Develop (de)activate account function ∙ Develop update account function ∙ Develop change access account function | Administrators ability to manage accounts (create, activate, deactivate, update, change access)
Manage Accounts | 2 | 2 | 3 | 2.1667 | 3 - Testing | ∙ Test UI ∙ Test create account function ∙ Test (de)activate account function ∙ Test update account function ∙ Test change access account function | Administrators ability to manage accounts (create, activate, deactivate, update, change access)
Reassign Leads | 1 | 2 | 3 | 2 | 1 - Requirements/Design | ∙ Define process ∙ Design lead reassignment UI | Reassign leads to other sales reps
Reassign Leads | 1 | 2 | 4 | 2.1667 | 2 - Development | ∙ Develop lead reassignment UI ∙ Develop lead reassignment function | Reassign leads to other sales reps
Reassign Leads | 1 | 1 | 2 | 1.1667 | 3 - Testing | ∙ Test lead reassignment UI ∙ Test lead reassignment function | Reassign leads to other sales reps
Train Sales Associates | 2 | 3 | 6 | 3.3333 | 4 - Prep | ∙ Identify training needs ∙ Create materials | Train on new system and processes
Train Sales Associates | 2 | 3 | 5 | 3.1667 | 5 - Conduct | ∙ Conduct training ∙ Follow up on training | Train on new system and processes
Train Sales Support | 2 | 3 | 6 | 3.3333 | 4 - Prep | ∙ Identify training needs ∙ Create materials | Train on new system and processes
Train Sales Support | 2 | 3 | 5 | 3.1667 | 5 - Conduct | ∙ Conduct training ∙ Follow up on training | Train on new system and processes
Train the Trainer | 3 | 4 | 6 | 4.1667 | 4 - Prep | ∙ Identify training needs ∙ Create materials | Train the trainer on new system and processes
Train the Trainer | 1 | 2 | 3 | 2 | 5 - Conduct | ∙ Conduct training | Train the trainer on new system and processes
Update Leads | 2 | 2 | 4 | 2.3333 | 1 - Requirements/Design | ∙ Define process ∙ Design update lead UI | Sales reps update lead statuses
Update Leads | 2 | 4 | 4 | 3.6667 | 2 - Development | ∙ Develop update lead UI ∙ Develop update lead function | Sales reps update lead statuses
Update Leads | 1 | 1 | 2 | 1.1667 | 3 - Testing | ∙ Test update lead UI ∙ Test update lead function | Sales reps update lead statuses
UW Report | 4 | 5 | 9 | 5.5 | 1 - Requirements/Design | ∙ Design report | Create UW report to send to the client (sending is manual)
UW Report | 5 | 10 | 14 | 9.8333 | 2 - Development | ∙ Transform data ∙ Create report ∙ Create ability to run report | Create UW report to send to the client (sending is manual)
UW Report | 3 | 5 | 10 | 5.5 | 3 - Testing | ∙ Test ability to run report ∙ Test report format ∙ Validate accurate results | Create UW report to send to the client (sending is manual)
View Lead | 2 | 4 | 5 | 3.8333 | 1 - Requirements/Design | ∙ Identify data to display ∙ Design view lead UI | Ability to review lead details
View Lead | 2 | 3 | 5 | 3.1667 | 2 - Development | ∙ Develop view lead UI ∙ Develop view lead functionality | Ability to review lead details
View Lead | 1 | 2 | 3 | 2 | 3 - Testing | ∙ Test view lead UI ∙ Test view lead functionality | Ability to review lead details
Template provided courtesy of The BA Guide
www.TheBAGuide.com