## ProjectSchedule
Sample Project
Company XYZ
Jeremy Aschenbrenner |  |  | Project Start: | 2018-08-01
|  |  | Display Week: | 1 |  |  | 2018-07-30 | [6 empty] | 2018-08-06 | [6 empty] | 2018-08-13 | [6 empty] | 2018-08-20 | [6 empty] | 2018-08-27 | [6 empty] | 2018-09-03 | [6 empty] | 2018-09-10 | [6 empty] | 2018-09-17
 | time axis 2018-07-30 to 2018-09-23
TASK | ASSIGNED TO | EST DURATION | PROGRESS | START | END | DAYS | time axis 2018-07-30 to 2018-09-23
Project Planning
Requirements Management Plan | Name | 2 | 0% | 2018-08-01 | 2018-08-03 | 3
Define Project Details | Name | 4 | 0% | 2018-08-06 | 2018-08-09 | 4
Stakeholder Analysis | Name | 2 | 0% | 2018-08-10 | 2018-08-13 | 4
Set Performance Measures | Name | 1 | 0% | 2018-08-10 | 2018-08-10 | 1
Finalize Plan | Name | 1 | 0% | 2018-08-14 | 2018-08-14 | 1
Project Design
Task 1 | Name | 2 | 0% | 2018-08-16 | 2018-08-17 | 2
Task 2 | Name | 5 | 0% | 2018-08-20 | 2018-08-24 | 5
Task 3 | Name | 1 | 0% | 2018-08-24 | 2018-08-24 | 1
Task 4 | Name | 3 | 0% | 2018-08-24 | 2018-08-28 | 5
Task 5 | Name | 4 | 0% | 2018-08-29 | 2018-09-03 | 6
Solution Creation
Task 1 | Name | 10 | 0% | 2018-09-05 | 2018-09-18 | 14
Task 2 | Name | 8 | 0% | 2018-09-19 | 2018-09-28 | 10
Task 3 | Name | 12 | 0% | 2018-09-19 | 2018-10-04 | 16
Task 4 | Name | 14 | 0% | 2018-10-01 | 2018-10-18 | 18
Task 5 | Name | 6 | 0% | 2018-10-19 | 2018-10-26 | 8
Testing
Task 1 |  |  | 0%
Task 2 |  |  | 0%
Task 3 |  |  | 0%
Task 4 |  |  | 0%
Task 5 |  |  | 0%
Implementation
Task 1 |  |  | 0%
Task 2 |  |  | 0%
Task 3 |  |  | 0%
Task 4 |  |  | 0%
Task 5 |  |  | 0%
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Note on I6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.